## Sheet1
Risk No. | Risk item | Effect | Cause | Probability | Severity | Actions to Minimize Risks | Final review
Project Planning
1.1.1 | Setting unrealistic deadlines and milestones | Poor planning and authorisation with clients can damage relationship with clients and team members. This will also have effects on some of the development as features and architecture will not be properly researched and designed. | • Poor planning and communication between parties | 2 | 4 | Provide realistic deadlines to clients, plan ahead which allows more time for development, give yourself enough time to complete your tasks. | Whilst this issue did arise halfway through development, It was quickly resolved by focusing and solely trying to achieve the MVP.
1.1.2 | Agreeing unrealistic targets | Prioritising features that are either unobtainable or unnecessary can not only effect the quality of the end product, but also showcases poor management of product expectations and can effect internal relations with clients. | • Promising features that are Otherwise unachievable. | 2 | 4 | • Be realistic with the features and functionality of your project, • Set up transparent communication channels with clients/developers, • Manage expectations and emotions of your clients in reference to their experience and knowledge of the projects themes. | The targets set were good. I wanted to do something different to distinguish my app from others but the MVP requirements were fair and achieved.
1.1.3 | Poor judgement of ability | Inability to complete tasks due to lack of knowledge can strongly impact the quality and the chance of deliverance of the project. This can also result in a poor relationship with management/clients and will most likely result in expulsion from the project and course. | • Lack of commitment to learning material, • Poor training from trainers, • Poor implementation of learned methodologies. | 1 | 4 | • Arrive on time to every training period, • Full application to provided training materials, • Practice learned materials in personal time. • Assign targets according to your own ability, • Engagement with trainers and colleagues on encountered problems. | Whilst various tasks were most certainly more difficult than others, there was more than enough support provided for me to achieve the majority of my goals during this project lifecycle.
1.1.4 | Change in project specification | Depending on the change in time-frame, as well as the seriousness of said change, this would massively affect the project from all aspects from architecture to the methodologies used. | • Change in requirements/time-frame from internal/external sources. | 3 | 4 | • Implement plans ahead of time to ensure that the MVP is achieved. • Prioritise the basics that will make up a functional project. • Organise a deadline extension for the project if needed. | The time-frame for project completion changed multiple times over the project’s lifespan, which impacted additional features to the project, however the MVP was still achieved.
Project Development
1.2.1 | Poor accessibility to appropriate software/ hardware | Poor or no access to related hardware and/or software can effect both the accessibility of project files, as well as the progression towards expected milestones. | • Limited access to sufficient machines, • little to no cloud storage capability, • Downtime on related services | 2 | 3 | Provide access and resources to efficient hardware and software that allow developers to fulfill projects. Set up remote access to related platforms and documents. | Due to some things not being covered in-time, this was not an issue during this project.
1.2.2 | SQL Injection Attacks | Common hacking technique that allows an attacker to read a database without authorisation, and can allow them to drastically change or destroy a database, resulting in inefficiency of project deliverables. | • Unsanitised input boxes and allowing SQL statements to be passed directly to the database | 2 | 5 | Use single quote characters and examine database for errors and anomalies, use sanitised queries instead of string concatenation. | I found no issues during my testing.
1.2.3 | DDoS/Network Attack | Downtime for either our internal network or the networks of the sites and services we use can result in little to no access to systems needed to progress project. Direct DDoS attacks can prevent internet access and may also reveal flaws of business networks, resulting in further attacks | Multiple systems flood the the bandwidth of a targetted system. Frequent for larger service providers (e.g: Cloudflare) | 2 | 4 | Whilst most larger service providers will have these measures in place to protect from these attacks, businesses like ourselves can build redundancy into network infrastructure and deploy anti DDoS hardware and software modules to make it harder for attacks. | There were no issues during the uptime of the project.
Health and Conditioning
1.3.1 | Possibility of illness | Falling ill during both the planning and development phases of the project can result in a loss of time, as well as a drop in quality for the project | Poor Hygiene, poor diet, stress | 1 | 2 | Continue with basic hygiene routine, eat/drink enough, take frequent breaks, use prescribed medicines if applicable, provide enough time to catch up with work. | This was not an issue during development
1.3.2 | Eye Strain | Eye strain can have potential effects on the quality of work produced, and could effect the chance of meeting deadlines for deliverables | Heavy Screen time, not taking frequent breaks from computer | 1 | 1 | Abide and respect breaks issued by QA. | This was not an issue during development, with enough breaks provided
1.3.3 | Posture/Ergonomics related issues | issues regarding posture and lack of ergonic support can not only affect the long term health of a developer, it can also affect the standard of work produced due to the undesireale conditions of the developer. | Heavy Screen time, not taking frequent breaks from computer | 1 | 2 | Provide developer(s) with suitable ergonic support such as workchairs, wrist supports ect.. Abide and respect breaks issued by QA. | This was not an issue during development, with enough breaks and equipment provided
1.3.4 | Disruption caused by catastrophic world events | Depending on the severity of measures put in place by either the client or the government, some of the other issues stated prior could be escalated to high severity. Likely risks include illness, isolation, little access to work content and even possible closure of project. | Contagious illness Catastrophic events Death | 5 | 5 | Ensure that has been protocols made to ensure productivity at home or at remote locations. Establish remote communication links and potentially adjust the goals and targets to match the severity of the current scenario. | This was not an issue during development
*: both Probability and Severity of this issue will depend on notice period compared to original deadline
*: severity and probability of impact to the project.
Key: Likelihood and Impact Scale uses a 1-5 scale, with 1 being not very strong and 5 being very strong